## Summary
Tester: | Mohanarao Maddala |  | Last Update: | 2021-08-23 |  |  | Last Review By:
FAIL | 11 | Open Defects | 5
PASS | 41 | Closed Defects | 0
NOT RUN | 13 | Total | 5
BLOCK | 0
NOT APPLICABLE | 0
Total | 65
ACC Matrix
Components |  |  | Attributes | [5 empty] | General
Sprint | Feature | Story | Secure | Compliance | Auditable | Reliable | Accessible | Responsive | Status | Comments
Sprint1 | Landing Page | Registration | 4 | 6 | 1 | 0 | 1 | 3 | Done
Sprint1 | Landing Page | Login | 2 | 1 | 3 | 0 | 1 | 3 | Done
Sprint1 | Landing Page | Popular Make | 0 | 1 | 0 | 0 | 0 | 0 | In Progress
Sprint1 | Profile | Basic Information | 1 | 2 | 3 | 0 | 1 | 3 | Done
Sprint1 | Profile | Additional Information | 2 | 9 | 3 | 0 | 1 | 3 | Done
Sprint1 | Profile | Change Password | 2 | 2 | 3 | 0 | 1 | 3 | Done
Sprint2 | Make | Make Information | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Make | Model List | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Model | Model Information | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Model | Votes | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Landing Page | Overall Rating | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Landing Page | Popular Model | 0 | 0 | 0 | 0 | 0 | 0 | Not Started

## Scenarios
Component | Attribute | Capability | Scenario | Status | Comments
Registration | Compliance | Registration Is Compliance | Back Ground :Given User navigates to Buggy car Website When User enters click on Register button Scenario :When User enters the data for below fields: Login, First Name, Last Name,Password,Confirm Password And User clicks on Register Button Then User should be to see the message "Registration is successful" | PASS | Back Ground :Given User navigates to Buggy car Website When User enters click on Register button
Registration | Compliance | Registration Is Compliance | When User clicks on cancel button Then User should be able to navigate to Landing Page | PASS
Registration | Compliance | Registration Is Compliance | When User clicks on Buggy car Top nav button Then User should be able to navigate to Landing Page | PASS
Registration | Compliance | Registration Is Compliance | When User is presented with an error message when attepting to register without providing Login details | PASS
Registration | Compliance | Registration Is Compliance | When User enters the different passwords for the fields "Password" and "Confirm Password" And User clicks on Register Button Then User should be to see the error message "Passwords do not match" | PASS
Registration | Compliance | Registration Is Compliance | When user enters the Username and Password And Click on Register Button Then Form is not clearing Previously Entered Cache details | FAIL | Form should clear cache of previously Entered details
Registration | Auditable | Registration Is Auditable | When User's run the Analytics on registration Screen Then User should see the interactions recorded for registration page as per requirement | NOT RUN | Anaytics Spec should be provided as part of requirement
Registration | Secure | Registration Is Secure | When User is trying to register with an existing user Then User should see the error message "UsernameExistsException: User already exists" | PASS
Registration | Secure | Registration Is Secure | When User is trying to register with special characters in the Login field Then User should see the error message | FAIL | User is able to create with special character including html tags
Registration | Secure | Registration Is Secure | When User is unable to register with a short password Then User should be able to see the error message "InvalidParameter: 1 validation error(s) found. - minimum field size of 6, SignUpInput.Password." | PASS
Registration | Secure | Registration Is Secure | When User is unable to register using lower case only in the password Then user should see the error message "InvalidPasswordException: Password did not conform with policy: Password must have uppercase characters" | PASS
Registration | Accessible | Registration Is Accessible | When User is running the Accessibility on Regesitration using axe cocunt Then All elements on the page are readable as per AAA Standards | FAIL | Car image should have an Alt attribute as per AAA standards
Registration | Responsive | Registration Is Responsive | When User can access website on mobile device screen | PASS
Registration | Responsive | Registration Is Responsive | When User can access website on tablet/ipad device screen | PASS
Registration | Responsive | Registration Is Responsive | When User can access website on laptop device screen | PASS
Popular Make | Compliance | Popular make is Complaince | Given User navigated to Buggar car Website When User Click On Popular Make And User tried to click on the Buggy rating link Then User should navigate to Home Page | FAIL | But, the link is not working.
Login | Compliance | Login Is Compliance | When User using valid credentials can login to Buggy cars | PASS
Login | Secure | Login Is Secure | When User with valid username but invalid password is unable to login to Buggy cars | PASS
Login | Secure | Login Is Secure | When User is unable to perform any kind of SQL injection | PASS
Login | Accessible | Login Is Accessible | When All elements on the page are readable | FAIL | The password element does not contains a label
Login | Responsive | Login Is Responsive | When User can access Login component on mobile device screen | PASS
Login | Responsive | Login Is Responsive | When User can access Login component on tablet/ipad device screen | PASS
Login | Responsive | Login Is Responsive | When User can access Login component on laptop device screen | PASS
Login | Auditable | Login Is Auditable | When User's Login interactions are recorded using analytics | NOT RUN
Login | Auditable | Login Is Auditable | When User's Login errors are recorded in error logs | NOT RUN
Login | Auditable | Login Is Auditable | When User's Login registration is recorded in Audit logs | NOT RUN
Basic Information | Compliance | Basic Information Is Compliance | When User clicks on the profile link and sees the following information in the Basic information section: Login - [User's login pre-populated] (Read Only) First Name [User's name pre-populated] (Editable) Last Name [User's Last pre-populated] (Editable) | PASS
Basic Information | Secure | Basic Information Is Secure | When User is unable to update basic information using special characters | FAIL | I was able to update basic informaiton with special character including html tags
Basic Information | Compliance | Basic Information Is Compliance | When User is unable to update basic information with a large string | PASS
Basic Information | Auditable | Basic Information Is Auditable | When User's Updates Basic information, interactions are recorded using analytics | NOT RUN
Basic Information | Auditable | Basic Information Is Auditable | When User's Updates Basic information with errors, these are recorded in error logs | NOT RUN
Basic Information | Auditable | Basic Information Is Auditable | When User's Updates Basic information is recorded in Audit logs | NOT RUN
Basic Information | Responsive | Basic Information Is Responsive | When User can access Basic information component on mobile device screen | PASS
Basic Information | Responsive | Basic Information Is Responsive | When User can access Basic information component on tablet/ipad device screen | PASS
Basic Information | Responsive | Basic Information Is Responsive | When User can access Basic information component on laptop device screen | PASS
Basic Information | Accessible | Basic Information Is Accessible | When All elements on the page are readable | PASS
Additional Information | Compliance | Additional Information Is Compliance | When User clicks on the profile link and sees the following information in the Additional information section: Gender [Empty - ON First login ] (Dropdown with Male and Female options) Age [Empty - ON First login ] (Numeric field only - range from 0 to 99 ) Address [Empty - On first login ] ( Open Text field ) Phone [Empty - On first login] (Numeric field only ) Hobby [Empty - On first login ] (Dropdown with multiple hobbies as option) | PASS
Additional Information | Compliance | Additional Information Is Compliance | When User is Unable to save Additional information with invalid Gender Long string | FAIL | Unhandle error message
Additional Information | Compliance | Additional Information Is Compliance | When User is Unable to save Additional information with invalid Age (Intruduce Characters or strings) | FAIL | Unhandle error message
Additional Information | Secure | Additional Information Is Secure | When User is Unable to save Additional information with invalid Age SPECIAL CHARACTERS | FAIL | Page displays "Get a candy ;) " as error message
Additional Information | Compliance | Additional Information Is Compliance | When User is Unable to save Additional information with invalid Gender Short String | FAIL | User is able to Save Additional information with Invalid Gender details
Additional Information | Compliance | Additional Information Is Compliance | When User is able to save Address | PASS
Additional Information | Compliance | Additional Information Is Compliance | When User is able to save valid Gender (Male/Female) | PASS
Additional Information | Compliance | Additional Information Is Compliance | When User is able to save with valid Age | PASS
Additional Information | Compliance | Additional Information Is Compliance | When User is able to save Valid Phone number | PASS
Additional Information | Compliance | Additional Information Is Compliance | When User is able to select a Hobby | PASS
Additional Information | Secure | Additional Information Is Secure | When User is Unable to save Additional information with invalid Address SPECIAL CHARACTERS | FAIL | I was allowed to introduce complete HTML section in the address field
Additional Information | Auditable | Additional Information Is Auditable | When User's Updates interactions are recorded using analytics | NOT RUN
Additional Information | Auditable | Additional Information Is Auditable | When User's Updates errors are recorded in error logs | NOT RUN
Additional Information | Auditable | Additional Information Is Auditable | When User's Updates are recorded in Audit logs | NOT RUN
Additional Information | Responsive | Additional Information Is Responsive | When User can access on mobile device screen | PASS
Additional Information | Responsive | Additional Information Is Responsive | When User can access on tablet/ipad device screen | PASS
Additional Information | Responsive | Additional Information Is Responsive | When User can access on laptop device screen | PASS
Additional Information | Accessible | Additional Information Is Accessible | When All elements on the page are readable | PASS
Change Password | Compliance | Change Password Is Compliance | When Users are able to update their password | PASS
Change Password | Secure | Change Password Is Secure | When User is unable to update password without providing actual password | PASS
Change Password | Secure | Change Password Is Secure | When User is unable to update password with wrong actual password | PASS
Change Password | Compliance | Change Password Is Compliance | When Users is unable to update password with new password missmatching the confirmation field | PASS
Change Password | Auditable | Change Password Is Auditable | When User's Updates interactions are recorded using analytics | NOT RUN
Change Password | Auditable | Change Password Is Auditable | When User's Updates errors are recorded in error logs | NOT RUN
Change Password | Auditable | Change Password Is Auditable | When User's Updates are recorded in Audit logs | NOT RUN
Change Password | Responsive | Change Password Is Responsive | When User can access on mobile device screen | PASS
Change Password | Responsive | Change Password Is Responsive | When User can access on tablet/ipad device screen | PASS
Change Password | Responsive | Change Password Is Responsive | When User can access on laptop device screen | PASS
Change Password | Accessible | Change Password Is Accessible | When All elements on the page are readable | PASS

## Defects
Defect # | Story/Component | Title | Steps | Tags | Status | Priority | Actions
D001 | Popular Make | Buggy rating Link is Not working from popular make page | 1. Login into https://buggy.justtestit.org . 2.Click On Popular Make 3. Then User tried to click on the Buggy rating link to navigate to the Home Page. But, the link is not working. | UI,Dev,Functional,Web,Sprint1 | Open | High
D002 | Registration | Form is not clearing cache of previous Entered details | 1. Navigate to https://buggy.justtestit.org . 2.Enter Login Name and password 3.And click on Registration button 4.Then Form is still showing previously Entered login details Expected Result: Form should clear cache of previously form details | UI,Dev,Functional,Web,Sprint1 | Open | High
D003 | Login | User is not able to Logged into Buggy car website if he forgets his password. | 1. Navigate to https://buggy.justtestit.org . 2.Enter Username and Wrong password 3. UI throws the error message which is Correct. However, there is no Forgot/Reset Password link for the User to logged in back for the Vote | UI,Dev,Functional,Web,Sprint1 | Open | High
D004 | Overall Rating | Ranking is Not working when the Votes are Equal | 1. Login into https://buggy.justtestit.org . 2.Give Same Votes to 2 different Models. 3. Then Both models are not displaying the same Rank. | UI,Dev,Functional,Web,Sprint1 | Open | High
D005 | Additional Information | Invaid Error Message "Get a candy ;) " displayed When User Input special characters in the Age Field | 1. Login with any valid user (User:bugcrgub, Password:Buggub@123) 2. Click on the Profile link in the top nav menu bar 3. In the Age field Type any special character for example "$$" 4. Save Additional information Actual Get a candy ;) error message is displayed Expected User should only be allowed to input digits between 1 and 99 | UI,Dev,Functional,Web,Sprint1 | Open | Medium | Low impact since customer is unable to save the form with invalid data